## Home
WFT 5.1c Workforce Excellence Action Plan™
Copyright © 2000 to 2020 AfCI LLC All Rights Reserved
OE21 Continuous Improvement Tool (Version 2020)
Warning: This computer program is protected by copyright law in the United States and international treaties including the Berne Convention. Unauthorized reproduction or distribution of this program, or any portion of it, may result in severe civil and criminal penalties, and will be prosecuted to the maximum extent possible under the law. For each instance in which a United States Court finds that infringement was committed willfully, the court in its discretion may increase the award of statutory damages to a sum of not more than $150,000.

## Example
Workforce Excellence Action Plan
This action plan is to implement a number of workforce issues that lead to high turnover and complaints. Reference Oe21 2.1 and 2.2 Strategy Development and Implementation.
Action Plan Summary:
| Orginal Project Start Date | 2013-04-02 |  | Responsibility: | Workforce Focus Team (WFT)
| Actual Project Start Date | 2013-04-05 |  | Date Updated: | 2017-04-30
| Orginal Project Completion Date | 2013-10-01
| Revised Project Completion Date | 2013-10-01
| Project Target Cost | 12468
| Revised Project Estimated Cost | 15000
|  | Performing | Labor or | Labor Rate | Resources | Task | Planned | Cumulative | Cumulative | Cumulative | Revised
|  | Organization | Non-Labor | or Non-Labor | Required | Completion | Completion | Planned | Actual | Planned $ | Completion
|  | Title or Code | Resources | Dollars | Dollars | Percentage | Dates | Completion | Completion | Consumed | Date
Task | Title <input> | <input> | <input> | <input> | <formula> | <input> | <input> | <formula> | <formula> | <formula> | <input>
1 | Conduct Workforce Satisfaction Assessment | WFT | 10 | 35 | 350 | 100% | 2013-04-15 | 2.807% | 2.807% | 350 | 2013-04-15
2 | Balance workload for overloaded units | WFT | 10 | 35 | 350 | 100% | 2013-04-23 | 5.614% | 5.614% | 700 | 2013-04-23
3 | Pinpoint reasons for turnover | WFT | 20 | 22 | 440 | 10% | 2013-04-30 | 9.143% | 5.967% | 1140 | 2013-05-10
4 | Reward low or no absenteeism workers | WFT | 20 | 35 | 700 |  | 2013-06-06 | 14.76% |  | 1840 | 2013-06-06
5 | Implement accident prevention program | WFT | 8 | 22 | 176 |  | 2013-06-10 | 16.17% |  | 2016 | 2013-06-15
6 | Setup a better complaint process | WFT | 16 | 22 | 352 |  | 2013-06-15 | 18.99% |  | 2368 | 2013-06-20
7 | Purchase a performance rewards system (software) | OFT | 0 | 5000 | 5000 |  | 2013-07-01 | 59.1% |  | 7368 | 2013-07-05
8 | Measure Improvement (Engagement/Satisfaction) | WFT | 8 | 35 | 280 |  | 2013-07-31 | 61.34% |  | 7648 | 2013-08-06
9 | Milestone 1 - Improved Workforce Engagement/Satisfaction | WFT | 1 | 35 | 35 |  | 2013-07-31 | 61.62% |  | 7683
10 | Conduct Workforce Capability Assessment | WFT | 8 | 35 | 280 |  | 2013-08-05 | 63.87% |  | 7963
11 | Identify low performers | WFT | 1 | 35 | 35 |  | 2013-08-06 | 64.15% |  | 7998
12 | Create plan to improve low performers | WFT | 16 | 35 | 560 |  | 2013-08-09 | 68.64% |  | 8558
13 | Identify worker capability for DanceSport service | WFT | 4 | 35 | 140 |  | 2013-08-10 | 69.76% |  | 8698
14 | Measure Improvement (workforce capability) | WFT | 8 | 35 | 280 |  | 2013-08-11 | 72.01% |  | 8978
15 | Milestone 2 - Improved Workforce Capacity | WFT | 1 | 35 | 35 |  | 2013-08-11 | 72.29% |  | 9013
16 | Conduct workforce capacity assessment | WFT | 8 | 35 | 280 |  | 2013-08-13 | 74.53% |  | 9293
17 | Identify workforce capacity needs | WFT | 1 | 35 | 35 |  | 2013-08-13 | 74.82% |  | 9328
18 | Retrain existing workforce to meet capacity needs | WFT | 40 | 35 | 1400 |  | 2013-08-25 | 86.04% |  | 10728
19 | Recruit new workers to meet current capacity needs | OFT | 16 | 65 | 1040 |  | 2013-08-27 | 94.39% |  | 11768
20 | Recruit DanceSport workforce to meet future needs | WFT | 16 | 35 | 560 |  | 2013-08-31 | 98.88% |  | 12328
21 | Measure Improvement (workforce capacity) | WFT | 4 | 35 | 140 |  | 2013-09-02 | 100% |  | 12468
22 |  |  |  |  | 0 |  |  |  |  | 12468
23 |  |  |  |  | 0 |  |  |  |  | 12468
24 |  |  |  |  | 0 |  |  |  |  | 12468
25 |  |  |  |  | 0 |  |  |  |  | 12468
26 |  |  |  |  | 0 |  |  |  |  | 12468
27 |  |  |  |  | 0 |  |  |  |  | 12468
28 |  |  |  |  | 0 |  |  |  |  | 12468
29 |  |  |  |  | 0 |  |  |  |  | 12468
30 |  |  |  |  | 0 |  |  |  |  | 12468
31 |  |  |  |  | 0 |  |  |  |  | 12468
32 |  |  |  |  | 0 |  |  |  |  | 12468
33 |  |  |  |  | 0 |  |  |  |  | 12468
34 |  |  |  |  | 0 |  |  |  |  | 12468
35 |  |  |  |  | 0 |  |  |  |  | 12468
36 |  |  |  |  | 0 |  |  |  |  | 12468
37 |  |  |  |  | 0 |  |  |  |  | 12468
38 |  |  |  |  | 0 |  |  |  |  | 12468
39 |  |  |  |  | 0 |  |  |  |  | 12468
40 |  |  |  |  | 0 |  |  |  |  | 12468
41 |  |  |  |  | 0 |  |  |  |  | 12468
42 |  |  |  |  | 0 |  |  |  |  | 12468
43 |  |  |  |  | 0 |  |  |  |  | 12468
44 |  |  |  |  | 0 |  |  |  |  | 12468
45 |  |  |  |  | 0 |  |  |  |  | 12468
46 |  |  |  |  | 0 |  |  |  |  | 12468
47 |  |  |  |  | 0 |  |  |  |  | 12468
48 |  |  |  |  | 0 |  |  |  |  | 12468
49 |  |  |  |  | 0 |  |  |  |  | 12468
50 |  |  |  |  | 0 |  |  |  |  | 12468
|  | TOTALS: | 216 |  | 12468
Note on N2: ACTION PLAN INSTRUCTIONS CREATE THE ACTION PLAN ACTION PLAN DESCRIPTION - Input Cell B3: Input a brief description of the Action Plan ORIGINAL PROJECT START DATE - Input Cell C6: Input the original project start date (DD-MMM-YY) ORIGINAL PROJECT COMPLETION DATE - Input Cell C8: Input the original project completion date (DD-MMM-YY) TASK TITLES - Input Cells B17-B66: Input the titles of all tasks to be completed (50 max) PERFORMING ORGANIZATIONS - Input Cells C17-C66: Input a code or short name for organizations that will perform the tasks LABOR HOURS - Input Cells D17-D66: Input labor hours for each Task that requires labor (people) NON-LABOR ZERO (0) - Input Cells D17-D66: Input a zero (0) for each Task that requires non-labor dollars (material, other costs) LABOR RATES - Input Cells E17-E66: Input labor rates per hour IF the task requires labor hours NON-LABOR DOLLARS Input Cells E17-E66: Input total dollars IF the task requires non-labor (material or other non-labor costs) PLANNED COMPLETION DATES - Input Cells H17-H66: Input task planned completion dates (DD-MMM-YY) for each task that is planned PROJECT TARGET COST - Cell C10 calculates the Project Target Cost (summary of dollars in Cells F17-F66) REVIEW - The Project Manager reviews all inputs to make sure they are correct, and then submits the plan to the Leadership Focus Team (LFT) for approval. APPROVAL -Before final LFT approval, the project manager incorporates any required changes and submits the plan to the LFT for final approval. MANAGE THE ACTION PLAN PROJECT START DATE: Before the Original Project Start Date (Cell C6) the project manager emails performing organizations to remind them to start the project on the Orginal Project Start Date (cell C6). ACTUAL PROJECT START DATE: When the project starts, input the Actuall Project Start Date in cell C7. STATUS: On date of task planned completion (Column H) obtain task completion status (0 to 100%) from performing organizations, and input the completion percent (%) in cells G11 to G66. REVISED COMPLETION DATES: Input Revised TASK Completion Date (if revised) into Cells L11-L66 REVISED PROJECT COMPLETION DATE - If necessary, input the Revised PROJECT Completion Date into Cell C9. REVISED PROJECT ESTIMATED COST: If necessary, input a new Revised Project Estimated Cost in Cell C11 MANAGE PROJECT TO THE END - Until the end of the project, make best efforts to complete the project on schedule and within budget. CLOSE THE ACTION PLAN - When all tasks are completed, the Action Plan is closed via email to performing organizations SHARING: Save the final plan and submit it to the LFT for distribution to those who will benefit from what has been learned. (End of Instructions)
Note on C6: Input date that action plan should start.
Note on C7: Input date that action plan should start.
Note on C8: Insert date that action plan started.
Note on C9: Insert date that action plan started.
Note on C11: Insert your latest estimate of final cost at completion of the plan.
Note on B17: Insert title of the task.
Note on C17: Insert title or code of the performing organization who will accomplish the task.
Note on D17: IF task requires labor hours, insert hours to do the task. IF task requires non-labor costs, insert a zero (0) in this cell.
Note on E17: IF task requires labor, insert labor hourly rate; IF task is non-labor insert dollar amount.
Note on G17: Insert task percentage of completion.
Note on H17: Insert date that task should be finished.
Note on L17: Insert date that task should be finished.

## Action Plan
Workforce Excellence Action Plan
Brief Description of action plan
Action Plan Summary:
| Orginal Project Start Date |  |  | Responsibility:
| Actual Project Start Date |  |  | Date Updated:
Orginal Project Completion Date
Revised Project Completion Date
| Project Target Cost | 0
Revised Project Estimated Cost
|  | Performing | Labor or | Labor Rate | Resources | Task | Planned | Cumulative | Cumulative | Cumulative | Revised
|  | Organization | Non-Labor | or Non-Labor | Required | Completion | Completion | Planned | Actual | Planned $ | Completion
|  | Title or Code | Resources | Dollars | Dollars | Percentage | Dates | Completion | Completion | Consumed | Date
Task | Title <input> | <input> | <input> | <input> | <formula> | <input> | <input> | <formula> | <formula> | <formula> | <input>
1 |  |  |  |  | 0 |  |  |  |  | 0
2 |  |  |  |  | 0 |  |  |  |  | 0
3 |  |  |  |  | 0 |  |  |  |  | 0
4 |  |  |  |  | 0 |  |  |  |  | 0
5 |  |  |  |  | 0 |  |  |  |  | 0
6 |  |  |  |  | 0 |  |  |  |  | 0
7 |  |  |  |  | 0 |  |  |  |  | 0
8 |  |  |  |  | 0 |  |  |  |  | 0
9 |  |  |  |  | 0 |  |  |  |  | 0
10 |  |  |  |  | 0 |  |  |  |  | 0
11 |  |  |  |  | 0 |  |  |  |  | 0
12 |  |  |  |  | 0 |  |  |  |  | 0
13 |  |  |  |  | 0 |  |  |  |  | 0
14 |  |  |  |  | 0 |  |  |  |  | 0
15 |  |  |  |  | 0 |  |  |  |  | 0
16 |  |  |  |  | 0 |  |  |  |  | 0
17 |  |  |  |  | 0 |  |  |  |  | 0
18 |  |  |  |  | 0 |  |  |  |  | 0
19 |  |  |  |  | 0 |  |  |  |  | 0
20 |  |  |  |  | 0 |  |  |  |  | 0
21 |  |  |  |  | 0 |  |  |  |  | 0
22 |  |  |  |  | 0 |  |  |  |  | 0
23 |  |  |  |  | 0 |  |  |  |  | 0
24 |  |  |  |  | 0 |  |  |  |  | 0
25 |  |  |  |  | 0 |  |  |  |  | 0
26 |  |  |  |  | 0 |  |  |  |  | 0
27 |  |  |  |  | 0 |  |  |  |  | 0
28 |  |  |  |  | 0 |  |  |  |  | 0
29 |  |  |  |  | 0 |  |  |  |  | 0
30 |  |  |  |  | 0 |  |  |  |  | 0
31 |  |  |  |  | 0 |  |  |  |  | 0
32 |  |  |  |  | 0 |  |  |  |  | 0
33 |  |  |  |  | 0 |  |  |  |  | 0
34 |  |  |  |  | 0 |  |  |  |  | 0
35 |  |  |  |  | 0 |  |  |  |  | 0
36 |  |  |  |  | 0 |  |  |  |  | 0
37 |  |  |  |  | 0 |  |  |  |  | 0
38 |  |  |  |  | 0 |  |  |  |  | 0
39 |  |  |  |  | 0 |  |  |  |  | 0
40 |  |  |  |  | 0 |  |  |  |  | 0
41 |  |  |  |  | 0 |  |  |  |  | 0
42 |  |  |  |  | 0 |  |  |  |  | 0
43 |  |  |  |  | 0 |  |  |  |  | 0
44 |  |  |  |  | 0 |  |  |  |  | 0
45 |  |  |  |  | 0 |  |  |  |  | 0
46 |  |  |  |  | 0 |  |  |  |  | 0
47 |  |  |  |  | 0 |  |  |  |  | 0
48 |  |  |  |  | 0 |  |  |  |  | 0
49 |  |  |  |  | 0 |  |  |  |  | 0
50 |  |  |  |  | 0 |  |  |  |  | 0
|  | TOTALS: | 0 |  | 0
Note on N2: ACTION PLAN INSTRUCTIONS CREATE THE ACTION PLAN ACTION PLAN DESCRIPTION - Input Cell B3: Input a brief description of the Action Plan ORIGINAL PROJECT START DATE - Input Cell C6: Input the original project start date (DD-MMM-YY) ORIGINAL PROJECT COMPLETION DATE - Input Cell C8: Input the original project completion date (DD-MMM-YY) TASK TITLES - Input Cells B17-B66: Input the titles of all tasks to be completed (50 max) PERFORMING ORGANIZATIONS - Input Cells C17-C66: Input a code or short name for organizations that will perform the tasks LABOR HOURS - Input Cells D17-D66: Input labor hours for each Task that requires labor (people) NON-LABOR ZERO (0) - Input Cells D17-D66: Input a zero (0) for each Task that requires non-labor dollars (material, other costs) LABOR RATES - Input Cells E17-E66: Input labor rates per hour IF the task requires labor hours NON-LABOR DOLLARS Input Cells E17-E66: Input total dollars IF the task requires non-labor (material or other non-labor costs) PLANNED COMPLETION DATES - Input Cells H17-H66: Input task planned completion dates (DD-MMM-YY) for each task that is planned PROJECT TARGET COST - Cell C10 calculates the Project Target Cost (summary of dollars in Cells F17-F66) REVIEW - The Project Manager reviews all inputs to make sure they are correct, and then submits the plan to the Leadership Focus Team (LFT) for approval. APPROVAL -Before final LFT approval, the project manager incorporates any required changes and submits the plan to the LFT for final approval. MANAGE THE ACTION PLAN ORIGINAL PROJECT START DATE: Before the Original Project Start Date (Cell C6) the project manager emails performing organizations to remind them to start the project on the Orginal Project Start Date (cell C6). ACTUAL PROJECT START DATE: When the project starts, input the Actuall Project Start Date in cell C7. STATUS: On date of task planned completion (Column H) obtain task completion status (0 to 100%) from performing organizations, and input the completion percent (%) in cells G11 to G66. REVISED COMPLETION DATES: Input Revised TASK Completion Date (if revised) into Cells L11-L66 REVISED PROJECT COMPLETION DATE - If necessary, input the Revised PROJECT Completion Date into Cell C9. REVISED PROJECT ESTIMATED COST: If necessary, input a new Revised Project Estimated Cost in Cell C11 MANAGE PROJECT TO THE END - Until the end of the project, make best efforts to complete the project on schedule and within budget. CLOSE THE ACTION PLAN - When all tasks are completed, the Action Plan is closed via email to performing organizations SHARING: Save the final plan and submit it to the LFT for distribution to those who will benefit from what has been learned. (End of Instructions)
Note on C6: Input date that action plan should start.
Note on C7: Input date that action plan should start.
Note on C8: Insert date that action plan started.
Note on C9: Insert date that action plan started.
Note on C11: Insert your latest estimate of final cost at completion of the plan.
Note on B17: Insert title of the task.
Note on C17: Insert title or code of the performing organization who will accomplish the task.
Note on D17: IF task requires labor hours, insert hours to do the task. IF task requires non-labor costs, insert a zero (0) in this cell.
Note on E17: IF task requires labor, insert labor hourly rate; IF task is non-labor insert dollar amount.
Note on G17: Insert task percentage of completion.
Note on H17: Insert date that task should be finished.
Note on L17: Insert date that task should be finished.